## Dashboard
ISO/IEC 42001:2023 · AI MANAGEMENT SYSTEM GAP ASSESSMENT
Powered by the OvikAI Three-Layer Assurance Framework · ovikai.com
Organisation
Assessment Date
Assessor Name
Lead Consultant
OVERALL COMPLIANCE STATUS
Status | Clauses | Annex A | Total | Percentage
Implemented | 0 | 0 | 0 | 0%
Partial | 0 | 0 | 0 | 0%
Not Implemented | 0 | 0 | 0 | 0%
N/A | 0 | 0 | 0 | 0%
TOTAL | 0 | 0 | 0 | 0%
GAPS BY PRIORITY
Priority | Clauses | Annex A | Total | Est. Days
High | 21 | 17 | 38 | 242
Medium | 6 | 14 | 20 | 64
Low | 0 | 1 | 1 | 2
TOTAL | 27 | 32 | 59 | 308
CERTIFICATION READINESS SCORE
Current Readiness | 0%
Target Score | 100%
Gap to Close | 100%
SCORE INTERPRETATION
Score Range | Status | What It Means
0% – 25% | Not ready | Major gaps across all areas. Do not attempt certification. Focus on foundational elements first.
26% – 50% | Early stage | Foundational elements partially in place. 12–18 months to certification readiness with focused effort.
51% – 75% | Progressing | Core requirements addressed. Gaps in operationalisation. 6–12 months to certification with the OvikAI programme.
76% – 90% | Advanced | Minor gaps. Certification feasible within 3–6 months. Focus on evidence documentation and audit readiness.
91% – 100% | Certification ready | Minor observations only. Proceed to stage 1 audit. Ensure all evidence is documented and accessible.
GAPS BY OVIKAĪ LAYER
Layer | Description | Clause Gaps | Annex A Gaps | Total Gaps
Layer 1 | Red Team & Assure | 0 | 0 | 0
Layer 2 | Register & Govern | 0 | 0 | 0
Layer 3 | Operate & Monitor | 0 | 0 | 0
All Layers | Foundation / All | 0 | 0 | 0

## Instructions
ISO/IEC 42001 Gap Assessment — How to Use This Template
OvikAI · Confidential — Presenter Use Only
HOW TO USE THIS TEMPLATE
Step 1 | Complete 'Organization Info' with client details and AI systems inventory.
Step 2 | In 'Clause Assessment', set Current Status for each clause using the dropdown. Override the pre-populated Priority if needed.
Step 3 | Document existing evidence. Be specific — name the document, version, and date.
Step 4 | Describe the gap. What specifically is missing or incomplete?
Step 5 | Override the Default Recommendation if the client context requires a different approach.
Step 6 | Repeat Steps 2–5 for 'Annex A Controls'.
Step 7 | Use the Dashboard to review the auto-calculated compliance score and layer breakdown.
Step 8 | Populate the Recommendations tab. Pre-populated items from high-priority gaps are a starting point — add client-specific actions.
NC CLASSIFICATION — What Each Level Means for Certification
Major NC | Critical for certification. An auditor WILL raise this as a major nonconformity. Certification is blocked until resolved. Address in Month 1–2.
Minor NC | Important but not blocking. An auditor WILL raise this as a minor NC. Corrective action plan required at certification. Address in Month 2–4.
Observation | Good to have. An auditor MAY comment on this. Not blocking certification but should be addressed for maturity. Address in Month 4–6.
OVIKAĪ LAYER MAPPING — How the Three Layers Address ISO 42001
Layer 1 — Red Team & Assure | Pre-deployment adversarial testing and impact assessment. Addresses: 6.1.1, 6.1.2, 6.1.3, 6.1.4, 8.2, 8.3, A.5.2, A.5.3, A.5.4, A.6.5, A.6.7.
Layer 2 — Register & Govern | Governed approval workflow and component registry. Addresses: 5.3, 6.3, 7.5, 8.1, 8.4, 9.2, A.2.3, A.3.2, A.4.3, A.6.2, A.6.3, A.6.6, A.7.5, A.9.3, A.9.4, A.10.2.
Layer 3 — Operate & Monitor | Runtime governance, audit trail, and post-market monitoring. Addresses: 6.2, 9.1, 10.1, 10.2, A.6.8, A.7.2, A.7.3, A.8.3, A.8.4, A.8.5, A.9.2, A.9.5, A.10.3.
Foundation / All Layers | Organisational foundation that all three layers depend on. Addresses: 4.1-4.4, 5.1, 5.2, 7.1-7.4, 9.3, A.2.2, A.3.3, A.4.2, A.4.4, A.8.2, A.10.4, A.10.5.

## Organization Info
ORGANISATION INFORMATION
CLIENT DETAILS
Organisation Name
Industry / Sector
Headquarters
Other Locations
Total Employees
AI / ML Team Size
AI Systems (Production)
AI Systems (Development / Evaluation)
Assessment Date
Assessor Name
Client Primary Contact
Existing Certifications
Reason for ISO 42001
Target Certification Date
Budget Allocated
AI SYSTEMS INVENTORY
System Name | Type | Risk Level | Status | Owner

## Clause Assessment
ISO 42001 CLAUSE ASSESSMENT · OvikAI Governed AI Factory Framework
Clause | Requirement | What to Check | OvikAI Layer | EU AI Act | NC Classification | Current Status | Evidence (if any) | Gap Identified | Priority | Effort (Days) | Recommendation (override if needed)
4.1 | Understanding the organisation and its context | Has the organisation documented internal and external issues that affect AI governance? Ask for: PESTLE or equivalent analysis with AI focus; regulatory landscape mapping; list of applicable AI laws by jurisdiction. | Foundation | All Articles | Major NC |  |  |  | High | 5 | Conduct a PESTLE analysis with AI focus. Document regulatory requirements (EU AI Act, GDPR, sector-specific). Review annually and after significant regulatory changes.
4.2 | Understanding needs of interested parties | Have all stakeholders been identified including affected persons (not just clients)? Ask for: stakeholder register; requirements per stakeholder; process for capturing affected persons (job applicants, patients, customers). | Foundation | Art.9, Art.13 | Major NC |  |  |  | High | 3 | Create an interested parties matrix. Include: clients, regulators, employees, affected persons, data subjects. Document AI-specific requirements per party. Update quarterly.
4.3 | Determining scope of AIMS | Is the AI Management System scope formally defined with boundaries and exclusions justified? Ask for: scope statement document; list of AI systems in scope; exclusions with written justification. | Foundation | All Articles | Major NC |  |  |  | High | 2 | Draft formal AIMS scope statement. List all AI systems in scope with version numbers. Document any exclusions with justified rationale. Obtain management sign-off.
4.4 | AI Management System | Is a formal AIMS established with documented processes and their interactions? Ask for: AIMS Manual or equivalent; process map showing interactions; evidence of system operation. | Foundation | Art.9 | Major NC |  |  |  | High | 10 | Design AIMS structure and produce an AIMS Manual. Define process interactions using a process map. Align with existing ISO 27001 or ISO 9001 structure if present.
5.1 | Leadership and commitment | Is top management demonstrably and actively committed to AIMS — not just in writing? Ask for: signed AI governance policy; board minutes referencing AI governance; resource allocation decisions; AI governance committee terms of reference. | Foundation | Art.9 | Major NC |  |  |  | High | 2 | Obtain formal CEO/Board commitment statement. Establish an AI Governance Board with defined terms of reference. Allocate dedicated budget. Hold monthly AI governance review meetings.
5.2 | AI Policy | Does a formal AI Policy exist that covers ethical principles, scope, prohibited uses, and responsibilities? Ask for: dated, signed AI Policy document; evidence it has been communicated to all staff; acknowledgement records. | All Layers | Art.9 | Major NC |  |  |  | High | 5 | Develop a comprehensive AI Policy covering: ethical principles, scope, prohibited uses, accountability, review cycle. Communicate to all staff. Publish externally where appropriate. Review annually.
5.3 | Organisational roles, responsibilities and authorities | Are specific AIMS roles defined with clear responsibilities — CAIO, AI Ethics Lead, Risk Manager? Ask for: RACI matrix for AI governance; job descriptions for AI governance roles; appointment letters or equivalent. | Layer 2 | Art.9 | Major NC |  |  |  | High | 3 | Appoint a Chief AI Officer (CAIO) or equivalent. Define AIMS Manager, AI Ethics Lead, and Risk Manager roles. Create RACI matrix. Communicate roles to the organisation.
6.1.1 | Actions to address risks and opportunities — General | Is risk-based thinking embedded in AIMS planning — not just addressed reactively? Ask for: documented process for identifying risks and opportunities; evidence it is applied during planning cycles. | Layer 1 | Art.9 | Major NC |  |  |  | High | 2 | Integrate risk-based thinking into all AIMS planning activities. Document the process for identifying AI risks and opportunities. Link to strategic planning cycle.
6.1.2 | AI risk assessment | Is there a documented process to identify, analyse, and evaluate AI risks across all systems? Ask for: AI risk assessment methodology; risk register with all AI systems; risk criteria; evidence of assessment being conducted. | Layer 1 | Art.9 | Major NC |  |  |  | High | 10 | Develop an AI risk assessment methodology covering: risk identification, likelihood/impact scoring, risk criteria, and risk register. Conduct assessment for all in-scope AI systems. Assign risk owners. Review quarterly for HIGH-RISK systems.
6.1.3 | AI risk treatment | Are risk treatment options formally selected with treatment plans and Statement of Applicability? Ask for: risk treatment plans per system; Statement of Applicability (SoA); evidence of treatment plan sign-off. | Layer 1 | Art.9 | Major NC |  |  |  | High | 5 | Develop risk treatment plans for all High and Critical risks. Produce Statement of Applicability mapping Annex A controls to assessed risks. Obtain management approval. Track treatment plan execution.
6.1.4 | AI system impact assessment | Have formal impact assessments been conducted evaluating consequences on individuals, groups, and society? Ask for: impact assessment reports per HIGH-RISK AI system; evidence of mitigation measures; sign-off by Data Protection Officer or equivalent. | Layer 1 | Art.9, Art.13 | Major NC |  |  |  | High | 15 | Conduct impact assessments for all HIGH-RISK AI systems. Cover: individual impacts, group differential impacts, societal impacts, and mitigation measures. Integrate with GDPR Data Protection Impact Assessment where applicable. Document and maintain.
6.2 | AI objectives and planning to achieve them | Are SMART objectives defined for AI governance with assigned owners, timelines, and resources? Ask for: documented AI objectives; measurable targets (e.g. bias reduction %, documentation coverage %); review records. | Layer 3 | Art.9 | Minor NC |  |  |  | Medium | 3 | Define at least 5 measurable AI governance objectives. Examples: 100% model card coverage by Q2; bias test pass rate >95%; zero undocumented AI systems in production. Assign owners, set timelines, and review quarterly.
6.3 | Planning of changes | Are changes to AIMS planned and managed — including model version updates and new AI system deployments? Ask for: change management procedure; evidence AI changes are reviewed before implementation; approval records. | Layer 2 | Art.9 | Minor NC |  |  |  | Medium | 2 | Integrate AI system changes into existing change management process. Define AI-specific change categories. Require AIMS Manager approval for all significant AI changes. Maintain a change log.
7.1 | Resources | Have adequate resources — budget, tools, personnel — been formally allocated for AIMS operation? Ask for: budget allocation document; headcount plan for AI governance roles; tooling procurement decisions. | Foundation | Art.9 | Major NC |  |  |  | High | 2 | Formalise resource allocation for AIMS. Define minimum team: CAIO, AIMS Manager, Ethics Lead. Procure required tools (bias testing, monitoring, documentation). Document annual budget with board approval.
7.2 | Competence | Are competence requirements defined for all roles affecting AI performance? Is training in place? Ask for: competence matrix; training records; responsible AI training programme; evidence of competence assessment. | Foundation | Art.9 | Major NC |  |  |  | High | 5 | Define competence requirements for all AI roles — technical and governance. Develop responsible AI training programme. Maintain training records. Include AI ethics in onboarding. Assess competence annually.
7.3 | Awareness | Are all personnel aware of the AI Policy, their contribution to AIMS, and consequences of non-compliance? Ask for: awareness session records; AI Policy acknowledgement logs; communication evidence. | Foundation | Art.9 | Minor NC |  |  |  | Medium | 2 | Run all-staff AI governance awareness sessions. Communicate AI Policy with acknowledgement. Include AI governance in new employee onboarding. Run annual refresher. Track completion rates.
7.4 | Communication | Is there a formal communication plan for AIMS — what is communicated, when, to whom, and how? Ask for: AIMS communication plan; evidence of internal communications; external communication records. | Foundation | Art.13 | Minor NC |  |  |  | Medium | 2 | Develop AIMS communication plan. Define: internal reporting cadence, stakeholder updates, regulator communications, public transparency disclosures. Assign communication owners.
7.5 | Documented information | Is documented information created, updated, and controlled — with version control and access management? Ask for: document control procedure; version history for key documents; evidence that all AI systems have documentation; document register. | Layer 2 | Art.12 | Major NC |  |  |  | High | 5 | Establish document control procedure. Create model cards for all production AI systems. Implement version control. Define document retention periods. Align with ISO 27001 document control if applicable.
8.1 | Operational planning and control | Are AI-specific operational controls in place — ethics gates in SDLC, outsourced process controls? Ask for: AI development lifecycle with governance gates; evidence of ethics review at each stage; controls for third-party AI development. | Layer 2 | Art.9 | Major NC |  |  |  | High | 10 | Integrate AI governance gates into SDLC. Define mandatory checkpoints: requirements review, bias assessment, ethics approval, deployment sign-off. Control outsourced AI development with contractual requirements.
8.2 | AI risk assessment (operational) | Are risk assessments conducted at planned intervals — quarterly for HIGH-RISK, annually for others — and after significant changes? Ask for: risk assessment schedule; evidence of periodic assessments; triggered assessment records after model changes. | Layer 1 | Art.9 | Major NC |  |  |  | High | 3 | Define risk assessment frequency: quarterly for HIGH-RISK systems, annually for MINIMAL/LIMITED risk. Mandate triggered assessments after: model version updates, data changes, significant incidents. Document and track.
8.3 | AI risk treatment (operational) | Is the risk treatment plan being actively implemented with evidence of control effectiveness? Ask for: treatment plan implementation records; control testing evidence; residual risk acceptance sign-off. | Layer 1 | Art.9 | Major NC |  |  |  | High | 15 | Implement all risk treatment controls from the treatment plan. Document evidence of implementation. Test control effectiveness. Record residual risk acceptance by appropriate authority. Track via risk register.
8.4 | AI system life cycle | Are AI system lifecycle processes formally managed — from design through decommissioning? Ask for: AI lifecycle policy; model cards for all systems; bias testing in CI/CD pipeline; human oversight mechanism; decommissioning procedure. | Layer 2 | Art.9, Art.12 | Major NC |  |  |  | High | 20 | Define AI system lifecycle stages and governance requirements at each stage. Create model cards for all systems. Integrate bias testing into CI/CD. Establish human review mechanism for HIGH-RISK decisions. Define decommissioning process.
9.1 | Monitoring, measurement, analysis and evaluation | Are KPIs defined and tracked for AIMS performance — bias metrics, model accuracy, incident rates, documentation coverage? Ask for: KPI dashboard; performance data; evidence of regular review; trend analysis. | Layer 3 | Art.12, Art.72 | Minor NC |  |  |  | Medium | 5 | Define AI governance KPIs including: bias incident rate, model accuracy drift, documentation coverage %, HITL override rate, mean time to incident detection. Create monitoring dashboard. Review monthly. Report to management quarterly.
9.2 | Internal audit | Is an internal audit programme in place covering AIMS? Are auditors trained? Have audits been conducted? Ask for: audit programme; auditor competence records; completed audit reports; corrective action tracking. | Layer 2 | Art.9 | Major NC |  |  |  | High | 5 | Establish AI governance audit programme. Train internal auditors on ISO 42001. Schedule at least one full AIMS audit before certification. Document findings and track corrective actions. Ensure auditor independence.
9.3 | Management review | Does top management formally review AIMS at planned intervals with documented inputs and outputs? Ask for: management review meeting records; review agenda template; decisions and action items from reviews. | Foundation | Art.9 | Major NC |  |  |  | High | 2 | Schedule quarterly AI governance management reviews. Define standard agenda: KPI review, risk status, audit findings, nonconformities, resource adequacy, improvement opportunities. Document decisions and actions. Track completion.
10.1 | Continual improvement | Is there a process for continually improving AIMS suitability, adequacy, and effectiveness? Ask for: improvement register; evidence that lessons from incidents are captured; improvement proposals and outcomes. | Layer 3 | Art.72 | Minor NC |  |  |  | Medium | 2 | Establish an improvement register. Capture lessons from AI incidents, near-misses, and audit findings. Track improvement proposals through to implementation. Report improvement outcomes in management review.
10.2 | Nonconformity and corrective action | Are nonconformities identified, documented, and addressed with root cause analysis and corrective actions? Ask for: nonconformity register; corrective action records (CARs); evidence of root cause analysis; effectiveness verification. | Layer 3 | Art.72 | Major NC |  |  |  | High | 3 | Implement a formal nonconformity and corrective action procedure. Create a nonconformity register. For each NC: document the finding, conduct root cause analysis, define corrective action, assign owner, set target date, verify effectiveness. Include AI incidents as nonconformities.

## Annex A Controls
ISO 42001 ANNEX A CONTROLS ASSESSMENT · OvikAI Governed AI Factory Framework
Control ID | Control Title | Control Description | Applicable? | OvikAI Layer | NC Classification | Status | Evidence (if any) | Gap | Priority | Effort (Days) | Recommendation
A.2.2 | AI policy | Policies for AI aligned with organisational policies | Yes | All Layers | Major NC |  |  |  | High | 5 | Create a formal AI Policy. Ensure alignment with existing information security and data governance policies. Cover: ethical principles, scope, prohibited uses, accountability, and review cycle.
A.2.3 | AI system policy | Document policies for each individual AI system | Yes | Layer 2 | Minor NC |  |  |  | Medium | 3 | Develop a one-page system policy for each production AI system covering: purpose, risk level, approved use cases, prohibited uses, and owner.
A.3.2 | Roles and responsibilities | Define roles for AI development and deployment with clear accountability | Yes | Layer 2 | Major NC |  |  |  | High | 3 | Define CAIO, AIMS Manager, AI Ethics Lead, and Risk Manager roles. Create RACI matrix. Publish role descriptions. Obtain formal appointments.
A.3.3 | Reporting to management | Establish formal reporting mechanisms to management for AI governance | Yes | Foundation | Major NC |  |  |  | High | 2 | Define AI governance reporting structure. Establish monthly AI Board reporting. Create standard report template covering: KPIs, incidents, risks, compliance status.
A.4.2 | Resourcing | Provide adequate resources for AI system lifecycle governance | Yes | Foundation | Major NC |  |  |  | High | 2 | Formalise governance resource allocation. Minimum: CAIO, AIMS Manager, Ethics Lead. Procure bias testing, monitoring, and documentation tools. Secure annual budget approval.
A.4.3 | Assigning of responsibilities | Assign competent persons as owners for each AI system | Yes | Layer 2 | Minor NC |  |  |  | Medium | 2 | Assign a named system owner for each production AI system. Document ownership in the agent registry. Include ownership in performance objectives.
A.4.4 | Allocation of resources | Allocate resources to each individual AI system lifecycle | Yes | Foundation | Minor NC |  |  |  | Medium | 2 | Define per-system resource allocation covering: maintenance budget, monitoring tooling, and governance overhead. Review annually.
A.5.2 | Assessing AI system impact on individuals | Formally assess consequences of AI decisions on individuals | Yes | Layer 1 | Major NC |  |  |  | High | 10 | Conduct individual impact assessments for all HIGH-RISK AI systems. Cover: decision accuracy impact, right of appeal, explanation provision, and remediation process. Document and maintain.
A.5.3 | Assessing AI system impact on groups | Assess differential impacts of AI on demographic groups | Yes | Layer 1 | Major NC |  |  |  | High | 8 | Conduct group impact assessments covering protected characteristics. Use fairness metrics (demographic parity, equalised odds). Document findings and mitigations. Re-assess after model changes.
A.5.4 | Processes for assessing potential biases | Establish and operate bias assessment processes | Yes | Layer 1 | Major NC |  |  |  | High | 10 | Implement bias testing in CI/CD pipeline using tools such as Fairlearn or AIF360. Define bias thresholds. Conduct bias assessment before every deployment. Document results and mitigations.
A.6.2 | Documentation of AI system | Maintain documentation throughout AI system lifecycle — model cards | Yes | Layer 2 | Major NC |  |  |  | High | 8 | Create model cards for all production AI systems. Cover: purpose, training data, performance metrics, known limitations, bias assessment results, version history. Maintain in a governed repository.
A.6.3 | Management of AI system development | Govern AI system development with defined controls and approval gates | Yes | Layer 2 | Minor NC |  |  |  | Medium | 5 | Add AI governance gates to SDLC: requirements review, bias assessment, ethics review, security review, deployment approval. Document approval evidence at each gate.
A.6.5 | Verification and validation | Conduct verification and validation of AI outputs including fairness testing | Yes | Layer 1 | Major NC |  |  |  | High | 5 | Implement a V&V process covering: functional testing, fairness testing, adversarial robustness testing, and performance validation against requirements. Document V&V results.
A.6.6 | Release and deployment | Enforce controls for AI system deployment — ethics approval gate required | Yes | Layer 2 | Major NC |  |  |  | High | 3 | Require CAIO or Ethics Lead approval before any production deployment. Document approval evidence. Implement a deployment checklist covering: model card complete, bias tests passed, risk treatment implemented.
A.6.7 | AI system security | Implement AI-specific security controls including adversarial attack protection | Yes | Layer 1 | Minor NC |  |  |  | Medium | 5 | Implement AI security controls: prompt injection protection, adversarial input detection, model theft prevention, output sanitisation. Integrate with existing information security programme.
A.6.8 | AI system maintenance | Monitor AI systems for drift and maintain post-deployment | Yes | Layer 3 | Major NC |  |  |  | High | 10 | Implement real-time monitoring for model drift, data distribution shift, and performance degradation. Define retraining triggers. Use tools such as Evidently AI or WhyLabs. Document monitoring results.
A.7.2 | Data acquisition | Acquire data consistently with intended purpose with documented provenance | Yes | Layer 3 | Minor NC |  |  |  | Medium | 3 | Document data sources for all AI systems. Record: source, collection date, licence, preprocessing steps, and limitations. Maintain a data provenance register.
A.7.3 | Data quality for AI systems | Establish and apply data quality criteria before training or inference | Yes | Layer 3 | Major NC |  |  |  | High | 8 | Define data quality criteria: completeness, accuracy, representativeness, freshness. Implement automated data quality testing. Document quality assessment results. Reject data that fails quality thresholds.
A.7.4 | Data labelling | Operate processes for labelling and annotation with bias review | Yes | Layer 1 | Minor NC |  |  |  | Medium | 3 | Define labelling standards and quality controls. Include bias review in labelling process. Assess inter-annotator agreement. Document labelling methodology and reviewer demographics.
A.7.5 | Data sets | Manage and analyse data sets for representativeness | Yes | Layer 2 | Minor NC |  |  |  | Medium | 5 | Conduct representativeness analysis for all training data sets. Document demographic coverage. Identify underrepresented groups. Maintain a data set register with version control.
A.8.2 | Information about responsible AI | Provide public information about responsible AI practices | Yes | Foundation | Observation |  |  |  | Medium | 3 | Publish an AI transparency report or responsible AI page on the organisation's website. Cover: AI systems in use, governance approach, bias mitigation, and contact for concerns.
A.8.3 | Disclosure of use of AI | Disclose use of AI to affected parties before or at point of interaction | Yes | Layer 3 | Major NC |  |  |  | High | 5 | Add AI disclosure to all user interfaces where AI makes or influences decisions. Disclosure must be clear, prominent, and understandable. Document disclosure method for each system.
A.8.4 | Information to operators and users | Provide information enabling safe use — explainability required | Yes | Layer 3 | Major NC |  |  |  | High | 8 | Implement explainability for HIGH-RISK AI decisions using techniques such as SHAP or LIME. Provide operators with model performance documentation. Train users on AI system capabilities and limitations.
A.8.5 | Information for affected individuals | Provide meaningful explanations to persons affected by AI decisions | Yes | Layer 3 | Major NC |  |  |  | High | 5 | Implement individual explanation mechanism for all automated decisions affecting individuals. Explanations must be meaningful and actionable. Provide appeal mechanism. Document the explanation process.
A.9.2 | Intended use | Monitor AI system alignment with its intended use — detect misuse | Yes | Layer 3 | Minor NC |  |  |  | Medium | 3 | Define intended use boundaries for each AI system. Implement monitoring for out-of-scope queries or uses. Log and review anomalous use patterns. Update intended use documentation as systems evolve.
A.9.3 | Human oversight of AI | Establish enforced human oversight mechanisms — not advisory policies | Yes | Layer 2 | Major NC |  |  |  | High | 10 | Implement technical human-in-the-loop controls for HIGH-RISK decisions. HITL must be enforced, not advisory. Define which decision types require human review. Log all human override decisions. Review override rates monthly.
A.9.4 | Override AI system outputs | Implement technical capability to override AI decisions | Yes | Layer 2 | Major NC |  |  |  | High | 8 | Implement technical override capability in all HIGH-RISK AI systems. Override must be available to authorised human reviewers. Log all override actions with reviewer ID, timestamp, and reason. Review override log monthly.
A.9.5 | Reporting concerns | Implement a mechanism for reporting AI concerns and incidents | Yes | Layer 3 | Minor NC |  |  |  | Medium | 3 | Create a named channel for reporting AI concerns (email, form, or hotline). Assign a responsible owner. Define response SLAs. Integrate with nonconformity process. Communicate the channel to all stakeholders.
A.10.2 | Terms and conditions for third-party AI | Address third-party AI governance in contracts | Yes | Layer 2 | Minor NC |  |  |  | Medium | 3 | Add AI-specific clauses to all third-party AI contracts. Cover: data usage, bias assessment, explainability, audit rights, incident notification, and liability. Review existing contracts and amend as required.
A.10.3 | Monitoring of third-party AI | Monitor third-party AI system performance and outputs | Yes | Layer 3 | Minor NC |  |  |  | Medium | 5 | Implement output monitoring for all third-party AI systems. Define acceptable performance thresholds. Review third-party AI performance quarterly. Escalate concerns to vendor.
A.10.4 | Providing information to third-party | Provide necessary information to third-party AI providers | Yes | Foundation | Observation |  |  |  | Low | 2 | Define what information must be provided to third-party AI providers: data descriptions, use context, privacy requirements, and performance expectations. Document in contracts.
A.10.5 | Customer agreements | Include AI terms and liability clauses in customer agreements | Yes | Foundation | Minor NC |  |  |  | Medium | 3 | Update customer contracts to include: AI use disclosure, liability limitations for AI decisions, data usage for AI training, customer rights regarding AI decisions, and contact for AI concerns.

## Recommendations
RECOMMENDATIONS & ACTION PLAN · OvikAI Gap Remediation Tracker
# | Ref | OvikAI Layer | NC Type | Gap / Finding | Recommended Action | Owner | Target Date | Effort (Days) | Status
1 | 5.2 | All Layers | Major NC | No AI Policy exists — no governance foundation | Draft AI Policy covering: ethical principles, scope, prohibited uses, accountability. Obtain CEO sign-off. Communicate to all staff within 30 days.
2 | 6.1.2 | Layer 1 | Major NC | No AI risk assessment process or risk register | Develop AI risk assessment methodology. Conduct assessment for all in-scope AI systems. Create risk register with owners and treatment plans.
3 | 6.1.4 | Layer 1 | Major NC | No impact assessments for HIGH-RISK AI systems | Conduct individual and group impact assessments for all HIGH-RISK systems. Integrate with GDPR DPIA process. Document mitigations.
4 | A.9.3 | Layer 2 | Major NC | No human oversight mechanism — automated decisions without review | Implement enforced HITL controls for HIGH-RISK AI decisions. Define which decisions require human review. Log all overrides.
5 | 5.3 | Layer 2 | Major NC | No CAIO or AI governance roles defined | Appoint CAIO or equivalent. Define AIMS Manager, Ethics Lead, and Risk Manager roles. Publish RACI matrix.
6 | 8.4 | Layer 2 | Major NC | No AI system lifecycle management — no model cards | Define AI lifecycle stages. Create model cards for all production systems. Integrate governance gates into SDLC.
7 | A.5.4 | Layer 1 | Major NC | No bias assessment process — bias not detected before deployment | Implement bias testing in CI/CD pipeline using Fairlearn or AIF360. Define bias thresholds. Mandatory pass before deployment.
8 | 9.2 | Layer 2 | Major NC | No internal audit programme for AIMS | Establish AI governance audit programme. Train internal auditors. Schedule at least one full audit before certification.
9 | A.6.8 | Layer 3 | Major NC | No drift monitoring or retraining triggers | Implement real-time monitoring for model drift and performance degradation. Define retraining triggers. Use Evidently AI or equivalent.
10 | 9.1 | Layer 3 | Minor NC | No KPIs defined for AI governance performance | Define KPIs: bias incident rate, model accuracy drift, documentation coverage %, HITL override rate. Create dashboard. Review monthly.
11 | 7.5 | Layer 2 | Major NC | No document control — models without documentation | Implement document control procedure. Create model cards for all systems. Version control all AI governance documents.
12 | A.8.3 | Layer 3 | Major NC | AI use not disclosed to affected parties | Add AI disclosure to all interfaces where AI makes or influences decisions. Disclosure must be clear and prominent.
13 | A.9.4 | Layer 2 | Major NC | No technical override capability for AI decisions | Implement override capability in all HIGH-RISK systems. Log all override actions with reviewer ID and reason.
14 | 10.2 | Layer 3 | Major NC | No nonconformity and corrective action process | Implement NC procedure. Create nonconformity register. Define root cause analysis process. Track CARs to closure.
15 | A.7.3 | Layer 3 | Major NC | No data quality criteria — biased data not detected | Define data quality criteria. Implement automated testing. Reject data failing quality thresholds. Document quality results.